## Arm Simulator Project
Task Name | Start Date | End Date | Raving Fan | Predecessors | Duration
ARM Simulator
Initial Database Setup | 2017-10-28 | 2017-10-28 |  |  | 1d
Initialize global array for all the registers (R0-R15). | 2017-10-28 | 2017-10-28 |  |  | 1d
Initialize global memory array. | 2017-10-28 | 2017-10-28 |  | 3SS | 1d
Initialize array to store all ARM commands. | 2017-10-28 | 2017-10-28 |  | 4SS | 1d
Initialize array to store all opcode's | 2017-10-28 | 2017-10-28 |  | 5SS | 1d
Implementing Stage Specific Functions | 2017-10-29 | 2017-11-19 |  |  | 21d
Make a Fetch function | 2017-10-29 | 2017-11-02 |  |  | 5d
Make a Decode function | 2017-10-29 | 2017-11-06 |  | 8SS | 8.25d
Make a Execute function | 2017-10-29 | 2017-11-10 |  | 9SS | 12.25d
Make a Memory access function | 2017-11-10 | 2017-11-12 |  | 10 | 2.75d
Make a Writeback function | 2017-11-10 | 2017-11-14 |  | 11SS | 4.75d
Testing | 2017-10-29 | 2017-11-18 |  | 8SS, 9SS, 10SS, 11SF, 12SF | 21d
Milestone | 2017-11-19 | 2017-11-19 |  |  | 0
Input File Handling | 2017-11-19 | 2017-11-21 |  |  | 3d
Read input file line by line and split about space | 2017-11-19 | 2017-11-21 |  |  | 3d
Fill the global memory array with instructions at indexes defined using their addresses. | 2017-11-19 | 2017-11-21 |  | 16SS | 3d
Testing / Bonus implementation | 2017-11-22 | 2017-11-29 |  |  | 8d
Testing / Bonus | 2017-11-22 | 2017-11-29 |  | 17, 16 | 8d

## Comments
Row 3 | Group management controls & notifications Add discussions or notes to any row. | Jenny Gruening | 06/26/13 6:09 AM
Row 5 | Improved console for IT manager Customers requesting easier to use console, especially in deployment | Jess Smart | 04/17/12 11:58 AM
| New survey released April 1, results close April 18 | Jess Smart | 04/17/12 11:59 AM